## Gantt Chart Team22
Team 22 | [26 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | CS6440 Team Project
PROJECT MANAGER | Mehul K Bhuva
[6 empty] | Team Sprint #2 | [6 empty] | Team Sprint #3 – Technical Presentation | [13 empty] | Team Sprint #4 – Development and Status Update | [13 empty] | Team Sprint #5 – Development and Status Update | [13 empty] | Team Sprint #6 – Progress Report Presentation | [13 empty] | Team Sprint #7 – Development and Status Update | [13 empty] | Team Sprint #8 – Project Submission
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
[6 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
Team Sprint #2 – Research, Planning & Requirements
Meeting with Mentors | Mehul K Bhuva | 2020-09-14 | 2020-09-21 |  | 100% | bar: Week 1 R
Meeting with Team | Mehul K Bhuva | 2020-09-14 | 2020-09-21 |  | 100% | bar: Week 1 R; Week 1 Su
Research | Pop Nanthakijjar / Joshua Metcalf | 2020-09-14 | 2020-09-21 |  | 100% | bar: Week 1 R to Week 1 Su
Project Plan | Mehul K Bhuva | 2020-09-14 | 2020-09-21 |  | 100% | bar: Week 1 R to Week 1 Su
Gantt Chart | Santha Bobbili | 2020-09-14 | 2020-09-21 | 7 | 100% | bar: Week 1 R to Week 1 Su
Project Plan Presentation | Jaison Saji Abraham | 2020-09-14 | 2020-09-21 |  | 100% | bar: Week 1 R to Week 1 Su
Introduction & Conclusion | Jaison Saji Abraham | 2020-09-14 | 2020-09-21 | 7 | 100% | bar: Week 1 R to Week 1 Su
Business Case | Jaison Saji Abraham | 2020-09-14 | 2020-09-21 | 7 | 100% | bar: Week 1 R to Week 1 Su
Narration | Jaison Saji Abraham | 2020-09-14 | 2020-09-21 | 7 | 100% | bar: Week 1 R to Week 1 Su
Submission | Mehul K Bhuva | 2020-09-14 | 2020-09-21 | 7 | 100% | bar: Week 1 Su
Team Sprint #3 – Technical Presentation
Research | Pop Nanthakijjar / Joshua Metcalf | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 2 T to Week 3 R
Architectural Diagram | Mehul K Bhuva / Santha Bobbili | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 2 F to Week 2 Su; Week 3 W to Week 3 R
Presentation | Jaison Saji Abraham | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 3 F to Week 3 Su
Narration | Jaison Saji Abraham | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 3 F to Week 3 Su
Gannt Chart Update | Santha Bobbili | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 3 R to Week 3 Su
Meeting with Mentors | Mehul K Bhuva | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 3 M; Week 3 R
Meeting with Team | Mehul K Bhuva | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 2 W; Week 2 Sa; Week 3 R
Submission | Mehul K Bhuva | 2020-09-22 | 2020-10-05 | 13 | 100% | bar: Week 3 Su
Team Sprint #4 – Development and Status Update
Research (Questions and Model) | Pop Nanthakijjar / Joshua Metcalf | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 T to Week 4 W
Setup Development Environment | Pop Nanthakijjar / Joshua Metcalf | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 T to Week 4 W; Week 4 Sa to Week 4 Su; Week 5 R to Week 5 Su
Front-End Development | Mehul K Bhuva / Pop Nanthakijjar | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 T to Week 4 W; Week 4 Sa to Week 4 Su; Week 5 R to Week 5 Su
Back-End Development | Santha Bobbili / Joshua Metcalf | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 T to Week 4 W; Week 4 Sa to Week 4 Su; Week 5 R to Week 5 Su
Testing and Q.A. | Santha Bobbili | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 T to Week 4 W; Week 4 Sa to Week 4 Su; Week 5 R to Week 5 Su
Progress Presentation | Mehul K Bhuva | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 Sa to Week 4 Su; Week 5 Sa to Week 5 Su
Gannt Chart Update | Santha Bobbili | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 F; Week 5 F
Narration | Mehul K Bhuva | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 Sa to Week 4 Su; Week 5 Sa to Week 5 Su
Meeting with Mentors | Mehul K Bhuva | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 M; Week 5 M
Meeting with Team | Mehul K Bhuva | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 R; Week 5 R
Submission | Mehul K Bhuva | 2020-10-06 | 2020-10-19 | 13 | 100% | bar: Week 4 Su; Week 5 F; Week 5 Su
Team Sprint #5 – Development and Status Update
Research (Questions and Model) | Pop Nanthakijjar / Joshua Metcalf | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 F to Week 6 Su; Week 7 F to Week 7 Su
Front-End Development | Mehul K Bhuva / Pop Nanthakijjar | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 F to Week 6 Su; Week 7 F to Week 7 Su
Back-End Development | Santha Bobbili / Joshua Metcalf | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 F to Week 6 Su; Week 7 F to Week 7 Su
Testing and Q.A. | Santha Bobbili / Joshua Metcalf | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 F to Week 6 Su; Week 7 F to Week 7 Su
Progress Presentation | Mehul K Bhuva | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 F to Week 6 Su; Week 7 F to Week 7 Su
Gannt Chart Update | Santha Bobbili | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 Sa; Week 7 Sa
Narration | Joshua Metcalf | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 Sa; Week 7 Sa
Meeting with Mentors | Mehul K Bhuva | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 M
Meeting with Team | Mehul K Bhuva | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 W
Submission | Mehul K Bhuva | 2020-10-20 | 2020-11-02 | 12 | 100% | bar: Week 6 Su; Week 7 Su
Team Sprint #6 – Progress Report Presentation
Front-End Development | Mehul K Bhuva / Pop Nanthakijjar | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R to Week 8 Su; Week 9 R to Week 9 Su
Back-End Development | Santha Bobbili / Joshua Metcalf | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R to Week 8 Su; Week 9 R to Week 9 Su
Testing and Q.A. | Santha Bobbili / Pop Nanthakijjar | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R to Week 8 Su; Week 9 R to Week 9 Su
Progress Report Presentation | Joshua Metcalf | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R to Week 8 Su; Week 9 R to Week 9 Su
Narration | Joshua Metcalf | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R to Week 8 Su; Week 9 R to Week 9 Su
Gannt Chart Update | Santha Bobbili | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 Su; Week 9 Sa to Week 9 Su
Meeting with Mentors | Mehul K Bhuva | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 M; Week 9 M
Meeting with Team | Mehul K Bhuva | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 R; Week 9 R
Submission | Mehul K Bhuva | 2020-11-03 | 2020-11-16 | 13 | 100% | bar: Week 8 Sa to Week 8 Su; Week 9 Sa to Week 9 Su
Team Sprint #7 – Development and Status Update
Front-End Development | Mehul K Bhuva / Pop Nanthakijjar | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 M; Week 10 W to Week 10 Sa; Week 11 M; Week 11 W to Week 11 Su
Back-End Development | Santha Bobbili / Joshua Metcalf | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 T to Week 10 Su; Week 11 T to Week 11 Sa
Testing and Q.A. | Joshua Metcalf | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 W to Week 10 Sa; Week 11 T to Week 11 Sa
Presentation | Mehul K Bhuva | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 W to Week 10 F; Week 11 W to Week 11 F
Narration | Pop Nanthakijjar | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 W to Week 10 F; Week 11 W to Week 11 F
Gannt Chart Update | Santha Bobbili | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 Sa; Week 11 Sa
Meeting with Mentors | Mehul K Bhuva | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 10 M; Week 11 M
Meeting with Team | Mehul K Bhuva | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 11 Su
Submission | Mehul K Bhuva | 2020-11-17 | 2020-11-30 | 13 | 100% | bar: Week 11 Su
Team Sprint #8 – Project Submission
Front-End Development | Mehul K Bhuva / Pop Nanthakijjar | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 M to Week 12 W
Back-End Development | Santha Bobbili / Joshua Metcalf | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 M to Week 12 W
Testing and Q.A. | Joshua Metcalf | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 M to Week 12 W
Presentation | Mehul K Bhuva | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 T to Week 12 W
Narration | Pop Nanthakijjar | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 T to Week 12 W
Gannt Chart Update | Santha Bobbili | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 T to Week 12 W
Meeting with Mentors | Mehul K Bhuva | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 T to Week 12 W
Meeting with Team | Mehul K Bhuva | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 M
Application Deployment | Pop Nanthakijjar / Santha Bobbili | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 T to Week 12 W
Project Submission | Mehul K Bhuva | 2020-12-01 | 2020-12-03 | 2 | 100% | bar: Week 12 M to Week 12 W